## Sheet1
MINISTRY OF NATIONAL POLICIEC,ECONOMIC AFFAIRS,RESETTLEMET and REHABILITATION,NORTHERN PROVINCE DEVELOPMENT,VOCATIONAL TRAINING & SKILLS DEVELOPMENT and YOUTH AFFAIRS - 2019
S.No | GN Division | Total No of Houses | Unit cost per house | Total Allocation(Rs) | Physical Progress - No of Houses at Various Stages | [6 empty] | Overall Physical progress(%) | Financial Progress |  |  |  |  | Remarks
[5 empty] | Work Commonced Stage | Foundation Completed stage | Wall Level ongoing | Wall Level Completed stage | Roof on going | Roof Level Completed | Fully Completed |  | Allocation released to DS Divi. (RS.) | Cash imprest received (Rs) | Total Expenditure (Rs) | Overall Financial Progress (%) | Balance available in DS Divi.(Rs)
1 | Vellankulam | 6 | 995000 | 5970000 |  | 1 | 5 |  |  |  |  | 30% |  |  | 1200000 | 20.1005
2 | Paliyaru | 4 | 995000 | 3980000 | 3 | 1 | [5 empty] | 15% |  |  | 800000 | 20.1005
3 | Illuppaikadavai | 6 | 995000 | 5970000 |  | 5 | 1 |  |  |  |  | 20% |  |  | 1200000 | 20.1005
4 | Anthoniyarpuram | 1 | 995000 | 995000 | 1 | [6 empty] | 15% |  |  | 200000 | 20.1005
5 | Kalliyadi | 3 | 995000 | 2985000 |  | 3 | [5 empty] | 30% |  |  | 600000 | 20.1005
6 | Koorai | 3 | 995000 | 2985000 | 3 | [6 empty] | 15% |  |  | 600000 | 20.1005
7 | Athimoddai | 3 | 995000 | 2985000 |  | 3 | [5 empty] | 15% |  |  | 600000 | 20.1005
8 | Kovilkulam | 2 | 995000 | 1990000 | 1 | 1 | [5 empty] | 15% |  |  | 400000 | 20.1005
9 | Vidaththalteevu / W | 2 | 995000 | 1990000 | 1 | 1 | [5 empty] | 15% |  |  | 400000 | 20.1005
10 | Vidaththalteevu / E | 1 | 995000 | 995000 |  | 1 | [5 empty] | 30% |  |  | 200000 | 20.1005
11 | Pallamadhu | 6 | 995000 | 5970000 |  | 6 | [5 empty] | 15% |  |  | 1200000 | 20.1005
12 | Kayanagar | 7 | 995000 | 6965000 | 7 | [6 empty] | 15% |  |  | 1400000 | 20.1005
13 | Periyamadhu West | 3 | 995000 | 2985000 | 1 | 1 |  | 1 |  |  |  | 15% |  |  | 600000 | 20.1005
14 | Pappamoddai | 3 | 995000 | 2985000 | 2 | 1 | [5 empty] | 15% |  |  | 600000 | 20.1005
15 | Veddayamurippu | 7 | 995000 | 6965000 |  | 7 | [5 empty] | 15% |  |  | 1400000 | 20.1005
16 | Malikaithidal | 1 | 995000 | 995000 |  | 1 | [5 empty] | 15% |  |  | 200000 | 20.1005
17 | Adampan | 5 | 995000 | 4975000 |  | 5 | [5 empty] | 15% |  |  | 1000000 | 20.1005
18 | Palaikuly | 2 | 995000 | 1990000 |  | 2 | [5 empty] | 15% |  |  | 400000 | 20.1005
19 | Nedunkandal | 4 | 995000 | 3980000 | 3 | 1 | [5 empty] | 15% |  |  | 1000000 | 25.1256
20 | Sornapury | 4 | 995000 | 3980000 |  | 4 | [5 empty] | 15% |  |  | 800000 | 20.1005
21 | Karunkandal | 2 | 995000 | 1990000 |  | 2 | [5 empty] | 30% |  |  | 200000 | 10.0503
22 | Andankulam | 3 | 995000 | 2985000 | 3 | [6 empty] | 15% |  |  | 600000 | 20.1005
23 | Kannaddy | 1 | 995000 | 995000 |  | 1 | [5 empty] | 15% |  |  | 200000 | 20.1005
24 | Alkatively | 3 | 995000 | 2985000 |  | 3 | [5 empty] | 15% |  |  | 600000 | 20.1005
25 | K/Vannakulam | 5 | 995000 | 4975000 | 1 | 4 | [5 empty] | 15% |  |  | 1000000 | 20.1005
26 | Kathankulam | 4 | 995000 | 3980000 | 2 | 2 | [5 empty] | 15% |  |  | 800000 | 20.1005
27 | Vaddakkandal | 4 | 995000 | 3980000 | 2 | 2 | [5 empty] | 15% |  |  | 800000 | 20.1005
28 | Palaipperumalkaddu | 7 | 995000 | 6965000 | 5 | 2 | [5 empty] | 15% |  |  | 1400000 | 20.1005
29 | Palaiyadipputhukulam | 2 | 995000 | 1990000 |  | 2 | [5 empty] | 15% |  |  | 400000 | 20.1005
30 | Parappukadanthan West | 2 | 995000 | 1990000 | 2 | [6 empty] | 15% |  |  | 400000 | 20.1005
Total |  | 106 |  | 105470000 | 37 | 62 | 6 | 1 |  |  |  | 15% |  |  | 21200000 | 20.1005